## Group Contribution Log
Course | CS3343
Term | 2022-23 Semester A
Project No. | Group 12
Project Name/Title | GoGoEat
No. of Team Members | 6
Project Manager Name | CHENG Yin
Student ID | Name (Last, First) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Total | Student | Relative | Contribution | e.g.Group Mark | Final Adjusted
56642520 | SONG Tao | 1 | 1 | 3 | 3 | 3 | 4 | 5 | 8 | 10 | 15 | 10 | 8 | 3 | 74 | SONG Tao | 1.016 | 100% | 80 | 80
56614557 | CHENG Yin | 1 | 1 | 3 | 3 | 3 | 4 | 5 | 8 | 10 | 15 | 10 | 8 | 3 | 74 | CHENG Yin | 1.016 | 100% | 80 | 80
56642728 | LUO Peiyuan | 1 | 1 | 3 | 3 | 3 | 4 | 5 | 8 | 10 | 15 | 10 | 8 | 3 | 74 | LUO Peiyuan | 1.016 | 100% | 80 | 80
56641511 | ZHOU Junchen | 1 | 1 | 3 | 3 | 3 | 4 | 5 | 8 | 10 | 11 | 11 | 11 | 3 | 74 | ZHOU Junchen | 1.016 | 100% | 80 | 80
56642741 | FENG Yong | 1 | 1 | 3 | 3 | 3 | 4 | 5 | 8 | 8 | 13 | 8 | 7 | 3 | 67 | FENG Yong | 0.91991 | 90.54% | 80 | 72.4324
56643530 | DU Wenxi | 1 | 1 | 3 | 3 | 3 | 4 | 5 | 8 | 10 | 15 | 10 | 8 | 3 | 74 | DU Wenxi | 1.016 | 100% | 80 | 80
| Total Effort | 6 | 6 | 18 | 18 | 18 | 24 | 30 | 48 | 58 | 84 | 59 | 50 | 18 | 437 | Max | 1.016 |  | Average | 78.7387
[19 empty] | Max | 80
[19 empty] | Min | 72.4324

## Weekly Activity Log
| Weekly Activity Log | Completed By
Week 1 | Recruit Project Memebers to Form a Team. | SONG Tao
Week 2 | Build Trust among Team Members, and List Possible Choices for the Domain of this Project | All Team
Week 3 | [1] Research & Analysis of requirements [2] Writing Use Case Diagram. | [1] All Team [2] CHENG Yin [2] DU Wenxi
Week 4 | [1] Writing Project Plan [2] Writing Class Diagram | [1] CHENG Yin [1] DU Wenxi [2] LUO Peiyuan [2] FENG Yong [2] SONG Tao [2] ZHOU Junchen
Week 5 | [1] Writing Use Case Diagram [2] Writing Class Diagram | [1] CHENG Yin [1] DU Wenxi [2] LUO Peiyuan [2] FENG Yong [2] SONG Tao [2] ZHOU Junchen
Week 6 | [1] Programming [2] Unit Testing | [1] CHENG Yin [1] LUO Peiyuan [1] SONG Tao [1] ZHOU Junchen [2] DU Wenxi [2] FENG Yong
Week 7 | [1] Programming - Phase 1 [2] Unit Testing | [1] CHENG Yin [1] LUO Peiyuan [1] SONG Tao [1] ZHOU Junchen [2] FENG Yong [2] DU Wenxi
Week 8 | [1] Programming - Phase 2 - Merge User Module with Login and Payment Module [2] Integration Testing | [1] CHENG Yin [1] LUO Peiyuan [1] SONG Tao [1] ZHOU Junchen [2] FENG Yong [2] DU Wenxi
Week 9 | [1] Programming - Phase 3 - Merge all including time and table management [2] Integration Testing [3] Regression Testing | [1][3] CHENG Yin [1][3] LUO Peiyuan [1][3] SONG Tao [1][3] ZHOU Junchen [2] FENG Yong [2] DU Wenxi
Week 10 | [1] Programming - Code Refactoring and Bug Fix [2] Integration Testing [3] Documentation [4] Regression Testing | [1][4]CHENG Yin [1][4]LUO Peiyuan [1][4]SONG Tao [2]DU Wenxi [2]FENG Yong [3]ZHOU Junchen
Week 11 | [1] Test Report [2] Bug Report [3] Documentation [4] Bug Fix and Regression Testing | [1][2] DU Wenxi [1][2] FENG Yong [2][3][4] CHENG Yin [2][4] LUO Peiyuan [2][4] SONG Tao [3][4] ZHOU Junchen
Week 12 | [1] Powerpoint [2] Self-reflection [3] Project Gantt Chart Reviewing [4] Activity Log Reviewing | [1][2][3][4] CHENG Yin [1][2] DU Wenxi [1][2] FENG Yong [1][2] LUO Peiyuan [1][2] SONG Tao [1][2] ZHOU Junchen
Week 13 | [1] Presentation | All Team